## Sheet1
Owner of Risk | Reason/Cause | Effect/Impact | Likelihood | Level (H, M, L) | Risk Prevention Strategy | Risk Contingency Plan
Current Team Lead | Technical Challenges | Potential unresolved technical issues leading to delays | Low | Low | Conduct regular technical reviews; seek opinions to solve issues | Develop a detailed plan and allocate extra time for technical challenges
Project Team | Integration Issues | Problems arising from subsystem integration | Medium | Medium | Develop a comprehensive integration plan and perform testing | Have a backup plan and additional testing if integration issues arise
Project Team | Task Delays | Team members may not meet task deadlines as planned | Medium | Medium | Set strict deadlines, monitor progress, adjust resources | Reallocate resources or extend deadlines as necessary
Current Team Lead | Scope Creep | Project scope may continuously expand, causing delays | Medium | Medium | Strictly control scope changes, require approvals | Review scope changes, assess impact, and adjust schedule accordingly
Project Team | Resource Allocation | Unequal distribution of work and responsibilities | Low | Low | Allocate tasks based on skill sets, ensure equal workload | Reallocate tasks and responsibilities to balance the workload
QA Engineer | Quality Assurance & Control | Failure to adhere to development standards | Medium | Medium | Establish coding standards, conduct regular code reviews | Identify and rectify quality issues through additional reviews
Team Lead | Change Management | Unplanned changes affecting scope, time, cost, and quality | Low | Low | Document change requests, assess impact, obtain approvals | Implement approved changes and update project documentation